## 10-Oct
| 8/Oct-10/Oct | Priority
Purpose | Adding assets (specifically enemies and portals) into test level in order to quickly and easily implement them for the real level(s)
Art | Finish enemy sprites,with animation: 1.Ghoul 2.Ghost 3.Skeleton | 1
| Color coordinate portals using border/ center | 2
Sound | Design sounds for each monster： 1.Ghoul 2.Ghost 3.Skeleton | 1
| Design sound for teleporting | 2
Program | Add enemies/enemy behaviour into test level | 1
| Add portals into test level so every direction is covered | 2
| Look into alternate camera work | 3

## 17-Oct
| 11/Oct-17/Oct | Priority
Purpose | Finish adding in all the assets needed for level design
Art | Sprites and animation for: 1.Victory goal 2.Key/Locked door 3.Lever | 1
| Animations for Raven: 1.Walking 2.Dying 3.Teleporting 4.Dashing 5.Invincibility | 2
Sound | Sound for： 1. level rotation 2.Victory 3.Lever 4.Key/Locked door | 1
| Sound for Raven's action | 2
| Work on how the music changes between planes | 3
Program | Implement: 1. level rotation 2.Victory 3.Lever 4.Key/Locked door | 1
| Implement Raven's action in game | 2

## 24-Oct
| 18/Oct-24/Oct | Priority
Purpose | Focus on animation and level building, and how to emphasize the veil.
Art | Finish environment art | 1
| Animations for Raven: 1.Walking 2.Dying 3.Teleporting 4.Dashing(veil jump) 5.Jumping | 2
Design | Design animation of Raven: 1.Walking 2.Dying 3.Teleporting 4.Dashing(veil jump) 5.Jumping | 1
| New level design with new mechanic | 2
Sound | Level 1 bgm Work on how the music changes between planes | 1
| Sound for Raven's action | 2
Program | Implement: 1.the behaviour of enemies. 2.dynamic switching between planes. 3.the new sounds in game. | 1
| Implement Raven's action in game | 2

## 31-Oct
| 25/Oct-31/Oct | Priority
Purpose | Focus on animation and level building, and how to emphasize the veil.Complete the main gaming content as soon as possible.
Art | Finish environment art: 1.Platform asset 2.Main background asset 3.End goal symbol | 1
| Animations for Raven: 1.Walking 2.Dying 3.Teleporting 4.Dashing(veil jump) 5.Jumping | 2
Design | Design the mechanic of dialog | 1
| Design the interface of game | 2
Sound | Level 1 bgm Work on how the music changes between planes | 1
| Sound for Raven's action | 2
Program | Implement: 1.new level building with new portal mechainism. 2.the behaviour of new enemies. 3.the new sounds in game. | 1
| Implement Raven's action in game | 2

## 07-Nov
| 1/Nov-7/Nov | Priority
Purpose | Focus on new mechanic and level building, finish the environment art and simple animation, try release the complete demo in 12 Nov
Art | Environment art: 1.Eastern temple style platform and background 2.End of goal | 1
| Animations for Raven: 1.Walking 2.Dying 3.Teleporting 4.Dashing(veil jump) 5.Jumping | 2
Design | Dialog mechanic | 1
| Soft tutorial in game | 2
Sound | Level main soundtrack | 1
| Sound for Raven's action | 2
Program | Implement: 1.the behaviour of enemies. 2.dialog mechanic | 1
| Implement Raven's action in game | 2