## Sheet1
No. | Feedback | Feedback date | Priority | Staff | Progress
1 | Character has way too much momentum (Martin) | 2018-10-05 | 3 | Michael Jonny | to do
2 | Veil jump is confusing (Martin) | 2018-10-05 | 3 | Michael Yang | to do
3 | reaction is slow (Martin) | 2018-10-09 | 3 | Michael Jonny | doing
4 | First plane in prototype tricky (Ken's son Duncan) | 2018-10-10 |  | Michael Jonny
5 | Really liked plane's mechanic (All of Ken's Sons) | 2018-10-10 |  | Michael Jonny
6 | Liked Veil Jump to get through gaps and found its purpose clear (All of Ken's sons) | 2018-10-10 |  | Michael Jonny
7 | Ken's son Duncan didn't like player momentum/slide, Kieran and Logan liked it. | 2018-10-10 |  | Michael Jonny
8 | More use of single jump vs double-jump, so that there is need of single jump Tolerance for gap, maybe slightly wider? (Justin) | 2018-10-11
9 | Jump/Portal animations will need to be quick and allow player to continue moving without having to wait for animations to complete (Grant) | 2018-10-11
10 | The veil requires context, animations must communicate relevance to player, there must be a connection between the veil jump and moving through portals. (Ewan) | 2018-10-11
11 | Must be a functional difference between planes, so as to require elegant solutions to puzzle-like elements (Ken) | 2018-10-11
12 | Found jumping over the skeleton to be difficult, weren't getting enough height (Keith & David) | 2018-10-11
13 | Raven = 'Tiny' - need to scale her up (Euan) | 2018-10-18
14 | The veil itself is still without context, it feels more like 'falling down an elevator' than moving between planes. (Ken) | 2018-10-18
15 | Concerns over game not being 'fun' ; being 'satisfying' might not be enough (Ken+Euan) | 2018-10-18
16 | How do we justify 'retro game' aesthetic? = Question of style (Ken) | 2018-10-18
17 | Raven = 'Looks like a penguin' (Euan) | 2018-10-18
18 | Does not like music, found it irritating (Euan) (music provided was a placeholder but in the style intended.) Music should reflect the brief closer: 'The Veil' would suggest lighter, more ethereal tonality. Will continue with Chiptune pallete (in-keeping with aesthetic) but work to have soundtrack more ambient and less in-your-face. | 2018-10-18
19 | Art style is good, but the level is not that interesting, because for now we don't have enemies to attack you and in game we don't know how to pass the level(no goal).The most frustrating thing is I can't kill the enemy in testing level.(Kiki) | 2018-10-18 |  | old version the veil
20 | Need a breadcrumb system to help player from getting lost (Frank Arnot-StormCloud) | 2018-10-25
21 | Player should be able to see and predict the consequence of their actions clearly, e.g project future platform location (Frank Arnot-StormCloud) | 2018-10-25
22 | Platforming elements felt good, but level could have more space (bumping head in confined areas) (Frank Arnot-StormCloud) | 2018-10-25
23 | Scripted Events sucg as dialogue will help provide context for player, such as what their goal is (Frank Arnot-StormCloud) | 2018-10-25
24 | Potentially have change in audio que when Raven on platform with coresponding plane, not when the change happens, so as to communicate to the player what the result will be? (Us) | 2018-10-25
25 | We kind of Want the player to get lost? The challenge will be making being lost fun (Us) | 2018-10-25
26 | Maybe retain chiptune instrumentation in the soundtrack, but supplement with organic instrumentation evocative of the tropes assigned to each plane (Us) | 2018-10-25
27 | If we get this to work it will be brilliant, the concept is there, we just need to ensure we communicate with the player enough (Frank Arnot-StormCloud) | 2018-10-25
28 | Summarising, that we need to improve Visual Grammer (Audio can help with this too) (Frank Arnot-StormCloud) | 2018-10-25
29 | Believes it will be fun, as solving puzzles is always satisfying, long as the player doesn’t become too frustrated to complete. (Frank Arnot-StormCloud) | 2018-10-25
30 | Requires some form of 'Soft-tutorial' to guide player at first, and then leave them to it, otherwise they may become frustrated before getting any enjoyment (David Hamilton - Ninja Kiwi) | 2018-10-25
31 | Begin work on the tutorial elements sooner rather than later, they may feel like a low priority task, but they are deceivingly difficult to do well and time-intensive (David Hamilton - Ninja Kiwi) | 2018-10-25
32 | We will only need this one level for the vertical slice (David Hamilton - Ninja Kiwi) | 2018-10-25
33 | Should we have some kind of hint system should the player take too long to progress? Need to not hold player's hand too much though (David Hamilton - Ninja Kiwi) | 2018-10-25
34 | If the game lacks a way for the player to make early progress then they might not get a chance to experience the really great parts of the game, have these elements sooner? (David Hamilton - Ninja Kiwi) | 2018-10-25
35 | Have something to highlight when player is near somehting they can interact with(David Hamilton - Ninja Kiwi) e.g an outline lighting up around the Lever? | 2018-10-25
36 | Game will go down well as long as its clear what player's goal is | 2018-10-25
37 | We're in a good place for Week#7 | 2018-10-25
38 | Should we wish to discuss game further, or starting up our own company and taking the game further he is open to meet up with us for coffee and a chat (David Hamilton - Ninja Kiwi) | 2018-10-25
39 | Keep it simple, we have a product at the moment, we just need to improve upon it (Graham & Ricardo - Outplay) | 2018-10-26
40 | Is the Veil jump a fundamental aspect of the game? Is it necessary? What does it add? (Graham & Ricardo - Outplay) | 2018-10-26
41 | Awesome Music! (Graham - Outplay) | 2018-10-26
42 | Does the frustration of veiljump detract from what is already good? The puzzle solving? (Graham & Ricardo - Outplay) | 2018-10-26
43 | If we include too many 'skill' elements in our game they detract from our puzzle elements and we isolate a smaller demographic (Graham & Ricardo - Outplay) | 2018-10-26
44 | Similar to Megaman, in that each section is its own unique puzzle, but needs to avoid frustrating player (Graham & Ricardo - Outplay) | 2018-10-26
45 | We need to find a balance between opposing puzzle and skill elements (Graham & Ricardo - Outplay) | 2018-10-26
46 | Avoid any timing pressures which could be frustrating (Graham & Ricardo - Outplay) | 2018-10-26
47 | Likes the concept for each plane's visual art-style - tropish (Graham & Ricardo - Outplay) | 2018-10-26
48 | If we are going to keep Veil Jump then we need to introduce it as a mechanic to player early on and make it worth keeping (Graham & Ricardo - Outplay) | 2018-10-26
49 | Will require much visual and audible cues to communicate with the player their progress, also, should there be a checkpoint system of some kind? (Graham & Ricardo - Outplay) | 2018-10-26
50 | Can complete the game with a "triple jump" before playing the game (resize/rescale?) Martin + Team | 2018-11-13
51 | Player needs more hand-holding than currently present, unaware of goal from beginning of game, and did not complete (Martin) | 2018-11-13
| "Tutorial" text box is infuriating, almost unpassable at first (Martin) | 2018-11-13
| Needs better signposting, and interactions between platforms button was wrongly noted (E instead of F) (Martin) | 2018-11-13
| Artwork is good and fits theme game's theme, though looking forward to new iterations and developments (Martin) | 2018-11-13
| Music (across all three themes) is great. (Martin) | 2018-11-13
| Jumping can be a bit distracting "jarring," so I need to find a way of making it less tiresome, maybe lower volume and add slight randomisation to pitch to start off with? (Martin) | 2018-11-13
| Audio issues, cutting out intermittingly (I think this could be to do with transitions between certain combinations of the planes and I can fix this with a bit of Wwise troubleshooting) (Martin) | 2018-11-13
| Loves the backstory, but feels it could be explored more in-game (Martin) | 2018-11-13
| Because the camera following the character everytime, when the player keep jumping, the camera will keep shaking, it makes player feel uncomfortable. | 2018-11-14
| Game title and menu looks too ugly. | 2018-11-14
Double jump requires fine touch, can't predict where Raven will land with the camera being so sharp and zoomed in. (Cian)
Aim for teaching the player new mechanics 3 times in 3 different ways. (Cian)
Really likes the mechanic, but feels like its dropped on the player, and this level is beyond tutorial level (Cian)
Needs a better sense of correct progress and direction (Cian)
Too much text, feels in general players ignore text (Cian)
The Lever needs to stand out better against the background (Martin)
Remaining time just making fixes and minor adjustments to do with sign-posting, be aware of what changes you would make, hypothetically and note them down, but this is outwith the scope of the deadline

## Sheet2
1 | to do
2 | doing
3 | done