## Sheet1
No. | Feedback | Feedback date | Priority | Staff | Progress
1 | Character has way too much momentum (Martin) | 2018-10-05 | 3 | Michael Jonny | to do
2 | Veil jump is confusing (Martin) | 2018-10-05 | 3 | Michael Yang | to do
3 | reaction is slow (Martin) | 2018-10-09 | 3 | Michael Jonny | doing
4 | First plane in prototype tricky (Ken's son Duncan) | 2018-10-10 |  | Michael Jonny
5 | Really liked plane's mechanic (All of Ken's Sons) | 2018-10-10 |  | Michael Jonny
6 | Liked Veil Jump to get through gaps and found its purpose clear (All of Ken's sons) | 2018-10-10 |  | Michael Jonny
7 | Ken's son Duncan didn't like player momentum/slide, Kieran and Logan liked it. | 2018-10-10 |  | Michael Jonny
8 | More use of single jump vs double-jump, so that there is need of single jump Tolerance for gap, maybe slightly wider? (Justin) | 2018-10-11
9 | Jump/Portal animations will need to be quick and allow player to continue moving without having to wait for animations to complete (Grant) | 2018-10-11
10 | The veil requires context, animations must communicate relevance to player, there must be a connection between the veil jump and moving through portals. (Ewan) | 2018-10-11
11 | Must be a functional difference between planes, so as to require elegant solutions to puzzle-like elements (Ken) | 2018-10-11
12 | Found jumping over the skeleton to be difficult, weren't getting enough height (Keith & David) | 2018-10-11
13 | Raven = 'Tiny' - need to scale her up (Euan) | 2018-10-18
14 | The veil itself is still without context, it feels more like 'falling down an elevator' than moving between planes. (Ken) | 2018-10-18
15 | Concerns over game not being 'fun' ; being 'satisfying' might not be enough (Ken+Euan) | 2018-10-18
16 | How do we justify 'retro game' aesthetic? = Question of style (Ken) | 2018-10-18
17 | Raven = 'Looks like a penguin' (Euan) | 2018-10-18
18 | Does not like music, found it irritating (Euan) (music provided was a placeholder but in the style intended.) Music should reflect the brief closer: 'The Veil' would suggest lighter, more ethereal tonality. Will continue with Chiptune pallete (in-keeping with aesthetic) but work to have soundtrack more ambient and less in-your-face. | 2018-10-18
19 | Art style is good, but the level is not that interesting, because for now we don't have enemies to attack you and in game we don't know how to pass the level(no goal).The most frustrating thing is I can't kill the enemy in testing level.(Kiki) | 2018-10-18

## Sheet2
1 | to do
2 | doing
3 | done