## Sheet1
| Due | Goal | Art Priority 1 | Art Priority 2 | Art Priority 3 | Sound Priority 1 | Sound Priority 2 | Sound Priority 3 | Program Priority 1 | Program Priority 2 | Program Priority 3
Build 1.1 | 2018-10-10 | Add assets into test level in order to quickly and easily implement them for the real level(s) | Finish enemy sprites (Ghoul, Ghost, Skeleton) | Color coordinate portals using border/ center | Environment assets, particularly a variety of platforms | Design sounds for each monster | Design sound for teleporting | Any other sounds in master list | Add enemies/enemy behaviour into test level | Add portals into test level so every direction is covered | Look into alternate camera work
Build 1.2 | 2018-10-17 | Finish adding in all the assets needed for level design | Sprites for: Victory goal, Key/Locked door, Lever | Walking/dying/teleporting/dashing animations for Raven | Other animations | Sound for level rotation | Finish any sounds on master sound list | Work on how the music changes between planes | Implement key/lock, victory | Level rotation | Work more on camera stuff
Build 1.3 | 2018-10-24 | Begin development of actual level(s). Refine and finalize art/sound assets. | Refine Raven/Enemy sprites, animations | Refine environment sprites | Conversation art | Finish any sound assets left (ask Mike) | Refine assets |  | Implement anything left that hasn’t been done yet | Build the real level | Start implementing conversations