## Sheet1
NAME | SCENE/SOUNDBANK | DESCRIPTION | TRIGGER | ASSET STATUS | Wwise STATUS | UNITY STATUS | PLAY | REVISION NOTES
VeilJump | Tveil_Lvl_SB | Warped Jump sound | 'W' Key | Complete | Implemented | Implemented | One-Shot
Jump | Tveil_Lvl_SB | Typical 8-bit Style | 'Spacebar' | Complete | Implemented | Implemented | One-Shot
Jump2 | Tveil_Lvl_SB | "^^^ w/but Pitched Up | '2ndSpacebar' | Complete | Implemented | Implemented | One-Shot
Ghoul1 | Tveil_Lvl_SB | Synthetic growl noise | Random playback when close proximity | RevisionNeeded | Implemented | Not implemented | RandomLoop | Too synthetic; Re-record as vocals, more' zombie'-like impression, then heavily process audio
Ghoul2 | Tveil_Lvl_SB | Synthetic growl noise | Random playback when close proximity | RevisionNeeded | Implemented | Not implemented | RandomLoop | Too synthetic; Re-record as vocals, more' zombie'-like impression, then heavily process audio
Ghoul3 | Tveil_Lvl_SB | Synthetic growl noise | Random playback when close proximity | RevisionNeeded | Implemented | Not implemented | RandomLoop | Too synthetic; Re-record as vocals, more' zombie'-like impression, then heavily process audio
Ghost1 | Tveil_Lvl_SB | Haunting & ethereal | Random playback when close proximity | Complete | Implemented | Not implemented | RandomLoop
Ghost2 | Tveil_Lvl_SB | Haunting & ethereal | Random playback when close proximity | Complete | Implemented | Not implemented | RandomLoop
Ghost3 | Tveil_Lvl_SB | Haunting & ethereal | Random playback when close proximity | Complete | Implemented | Not implemented | RandomLoop
DoorLocked | Tveil_Lvl_SB | Denied | 'E' Interact | Complete | Not implemented | Not implemented | One-Shot
DoorOpen | Tveil_Lvl_SB | Typical Door | 'E' Interact w/Key | Complete | Not implemented | Not implemented | One-Shot
GreenGoo | Tveil_Lvl_SB | Acidic, gutteral bubbling | Looped playback when close proximity | RevisionNeeded | Complete | Not implemented | Loop* | Bubbles too quickly and at too high a pitch; pitch down and reduce speed. Think beans or curry bubbling?
Key | Tveil_Lvl_SB | K'Ching! | Pickup' | Complete | Not implemented | Not implemented | One-Shot
Lever1 | Tveil_Lvl_SB | Satisfying Ratchet | 'E' Interact | Complete | Complete | Complete | One-Shot
Lever2 | Tveil_Lvl_SB | Satisfying Ratchet | 'E' Interact | Complete | Complete | Complete | One-Shot
BoneBoomerang | Tveil_Lvl_SB | Comedic/Mickey Mouse attack | Upon enemy attack, when nearby | AnimationReq'd | Not implemented | Not implemented | EnemyAttack | Perfect for now, will need to do some editing when animation is complete to ensure sound lasts correct time/ends correctly should it connect/miss
PortalA | Tveil_Lvl_SB | Raven Explodes and rematerialises | 'E' Interact | Complete | Complete | Complete | Stinger | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
PortalB | Tveil_Lvl_SB | Raven Explodes and rematerialises | 'E' Interact | Complete | Complete | Complete | Stinger | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
PortalC | Tveil_Lvl_SB | Raven Explodes and rematerialises | 'E' Interact | Complete | Complete | Complete | Stinger | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
RotatePlane | Tveil_Lvl_SB | Grinding, earth, then locking in place | Triggered in sequence after 'Lever' | AnimationReq'd | Not implemented | Not implemented | One-Shot | Perfect for now, will need to do some editing when animation is complete, likely have more of a fade-in?
RavenDeath | Tveil_Lvl_SB | Dematerialises into pixels and blow away | Player-Death | Complete | Not implemented | Not implemented | One-Shot
MenuLoop | Tveil_Menu_SB | Strange-religious chiptune | On menu-screen loop, Destroy on level-load | Complete | Complete | Complete | Loop
EndCredits | Tveil_Credits_SB | Positive 'You-did-it' chiptune | On Credits-list loop | Complete | Complete | Not implemented | Loop
TxtSpeech | Tveil_Lvl_SB | Bleep.bleep.bleep etc really fast. | * | AnimationReq'd | Not implemented | Not implemented | * | *Potentially not in finished game, will consider revisions should animations be provided.
LevelLoop1 | Tveil_Lvl_SB | Aztec/Mayan Tropes | Loops within plane 1 until player transitions to another. | Complete | Complete | Complete | Loop | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
LevelLoop2 | Tveil_Lvl_SB | Egyptian/Middle Eastern Tropes | Loops within plane 2 until player transitions to another. | Complete | Complete | Complete | Loop | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
levelLoop3 | Tveil_Lvl_SB | Far Eastern/Asian Tropes | Loops within plane 3 until player transitions to another. | Complete | Complete | Complete | Loop | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
S1_S2_Transition | Tveil_Lvl_SB |  | Player moves between Plane 1 and 2 | Complete | Complete | Complete | Transition | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
S1_S3_Transition | Tveil_Lvl_SB |  | Player moves between Plane 1 and 3 | Complete | Complete | Complete | Transition | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
S2_S1_Transition | Tveil_Lvl_SB |  | Player moves between Plane 2 and 1 | Complete | Complete | Complete | Transition | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
S2_S3_Transition | Tveil_Lvl_SB |  | Player moves between Plane 2 and 3 | Complete | Complete | Complete | Transition | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
S3_S1_Transition | Tveil_Lvl_SB |  | Player moves between Plane 3 and 1 | Complete | Complete | Complete | Transition | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
S3_S2_Transition | Tveil_Lvl_SB |  | Player moves between Plane 3 and 2 | Complete | Complete | Complete | Transition | Now the music slows down in speed with the current music track as it transitions between planes, I just need to get the speed right to sync with the game
|  | Fire Burning | Ambient burning w/Low pass | Incomplete | Not implemented | Not implemented | Loop*
|  | Boulder Rolling | To warn player it's a danger | AnimationReq'd | Not implemented | Not implemented | Loop*
|  | Ogre Grunts | Charging Ogre Aggressive | AnimationReq'd | Not implemented | Not implemented | One-Shot
|  | Progress Noise | When player places key platform | Incomplete | Not implemented | Not implemented | One-Shot
|  | UI Navigation | Typical Chiptune Nav | RevisionNeeded | Not implemented | Not implemented | One-Shot
|  | Aztec Ambience | Natural sounds to accompany ST | Incomplete | Not implemented | Not implemented |  | To be layered behind the 3 plane soundtracks, in order to phase in between planes with the same functionality (avoids more programming)
|  | Eastern Ambience | Natural sounds to accompany ST | Incomplete | Not implemented | Not implemented |  | To be layered behind the 3 plane soundtracks, in order to phase in between planes with the same functionality (avoids more programming)
|  | Egyptian Ambience | Natural sounds to accompany ST | Incomplete | Not implemented | Not implemented |  | To be layered behind the 3 plane soundtracks, in order to phase in between planes with the same functionality (avoids more programming)