## Sheet1
No. | Feedback | Feedback date | Priority | Staff | Progress
1 | Character has way too much momentum (Martin) | 2018-10-05 | 3 | Michael Jonny | to do
2 | Veil jump is confusing (Martin) | 2018-10-05 | 3 | Michael Yang | to do
3 | reaction is slow (Martin) | 2018-10-09 | 3 | Michael Jonny | doing
4 | First plane in prototype tricky (Ken's son Duncan) | 2018-10-10 |  | Michael Jonny
5 | Really liked plane's mechanic (All of Ken's Sons) | 2018-10-10 |  | Michael Jonny
6 | Liked Veil Jump to get through gaps and found its purpose clear (All of Ken's sons) | 2018-10-10 |  | Michael Jonny
7 | Ken's son Duncan didn't like player momentum/slide, Kieran and Logan liked it. | 2018-10-10 |  | Michael Jonny
8 | More use of single jump vs double-jump, so that there is need of single jump Tolerance for gap, maybe slightly wider? (Justin) | 2018-10-11
9 | Jump/Portal animations will need to be quick and allow player to continue moving without having to wait for animations to complete (Grant) | 2018-10-11
10 | The veil requires context, animations must communicate relevance to player, there must be a connection between the veil jump and moving through portals. (Ewan) | 2018-10-11
11 | Must be a functional difference between planes, so as to require elegant solutions to puzzle-like elements (Ken) | 2018-10-11
12 | Found jumping over the skeleton to be difficult, weren't getting enough height (Keith & David) | 2018-10-11

## Sheet2
1 | to do
2 | doing
3 | done